## Plan1
SISTEMA WEB DrogaNet
HORAS PREVISTAS | [7 empty] | TOTAL | HORAS REALIZADAS | [7 empty] | TOTAL | TAREFAS
HORAS TAREFAS | EVERTON | GUSTAVO | JULIO | LUÍS E. | LUÍS M. | MARCOS | PEDRO |  | HORAS TAREFAS | EVERTON | GUSTAVO | JULIO | LUÍS E. | LUÍS M. | MARCOS | PEDRO |  | T1 | BURN DOWN
| T3 | T1 / T4 | T4 | T2 | T4 | T4 | T5 |  |  | T3 | T5 | T1 | T2 | T4 | T4 | T5 |  | T2 | CRONOGRAMA
SEXTA | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 5 | SEXTA | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | T3 | STATUS REPORT
SABADO | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | SABADO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T4 | DESENVOLVIMENTO
DOMINGO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DOMINGO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T5 | REVISÃO GERAL
SEGUNDA | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 2 | SEGUNDA | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
TERÇA | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | TERÇA | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
QUARTA | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 3 | QUARTA | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
QUINTA | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 4 | QUINTA | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 5
TOTAL HORAS | 1 | 4 | 4 | 3 | 4 | 4 | 1 | 21 | TOTAL HORAS | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 11 |  | HORAS REALIZADAS
[6 empty] | PREVISTAS | REALIZADAS
[5 empty] | QUINTA | 21 | 21
[5 empty] | SEXTA | 16 | 19
[5 empty] | SABADO | 13 | 19
[5 empty] | DOMINGO | 13 | 19
[5 empty] | SEGUNDA | 11 | 18
[5 empty] | TERÇA | 9 | 16
[5 empty] | QUARTA | 6 | 15
[5 empty] | QUINTA | 2 | 10
[5 empty] | SEXTA | #REF! | #REF!
[5 empty] | SABADO | #REF! | #REF!
[5 empty] | DOMINGO | #REF! | #REF!
[5 empty] | SEGUNDA | #REF! | #REF!
[5 empty] | TERÇA | #REF! | #REF!
[5 empty] | QUARTA | #REF! | #REF!
[5 empty] | QUINTA | #REF! | #REF!
[5 empty] | SEXTA | #REF! | #REF!

## Cálculos (hidden)
*** Esta planilha deve permanecer oculta ***
|  |  |  | Produto | TRIMESTRE 1 | TRIMESTRE 2 | TRIMESTRE 3 | TRIMESTRE 4 | Total
| 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  | Outros | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | TOTAL | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!