## 16-09
SISTEMA WEB DE CONTROLE DE DROGARIAS
ATIVIDADES X TEMPO | [9 empty] | TOTAL
CONSTRUIR TELAS |  | HORAS | STATUS |  |  | QUEM? | INÍCIO | PREVISÃO | TÉRMINO | 143
| assinatura | 4 |  |  | DONE | MARCOS | 20/19/2016 |  | 21/19/2016
| cadastrar_creditos | 6 |  |  | DONE | JULIO | 20/19/2016 |  | 21/19/2016
| cadastrocliente | 6 |  |  | DONE | EVERTON | 20/19/2016 |  | 21/19/2016
| cadastrocliente_Admin | 6 |  |  | DONE | LUIS M | 20/19/2016 |  | 21/19/2016
| cadastrofornecedor | 6 |  |  | DONE | GUSTAVO | 20/19/2016 |  | 21/19/2016
| cadastrofuncionario_Admin | 6 | TODO |  |  | GUSTAVO |  | 30/19/2016
| cadastrofuncionario_User | 6 | TODO |  |  | GUSTAVO |  | 30/19/2016
| cadastroloja | 6 |  |  | DONE | JULIO | 20/19/2016 |  | 22/19/2016
| cadastromedicamento | 6 |  |  | DONE | MARCOS | 20/19/2016 |  | 22/19/2016
| cadastrorede | 2 | TODO |  |  | JULIO |  | 30/19/2016
| cadastrotipo | 2 | TODO |  |  | JULIO |  | 30/19/2016
| caixafinal | 2 | TODO |  |  | MARCOS |  | 30/19/2016
| estoque | 5 | TODO |  |  | GUSTAVO |  | 30/19/2016
| homeadmin | 5 |  | DOING |  | JULIO | 23/19/2016 | 30/19/2016
| homefuncionario | 5 |  | DOING |  | EVERTON | 23/19/2016 | 30/19/2016
| homegerente | 5 |  | DOING |  | LUIS | 23/19/2016 | 30/19/2016
| index | 7 | TODO |  |  | MARCOS |  | 30/19/2016
| listafuncionario | 6 | TODO |  |  | JULIO |  | 30/19/2016
| listaloja | 6 |  |  | DONE | JULIO | 20/19/2016 |  | 22/19/2016
| listamedicamentos | 7 | TODO |  |  | LUIS M |  | 30/19/2016
| login | 4 |  |  | DONE | LUIS | 20/19/2016 |  | 23/19/2016
| pricing | 4 |  |  | DONE | MARCOS | 20/19/2016 |  | 23/19/2016
| relatoriocliente | 7 | TODO |  |  | JULIO |  | 30/19/2016
| relatoriomedicamento | 7 | TODO |  |  | JULIO |  | 30/19/2016
| relatoriovenda | 7 | TODO |  |  | JULIO |  | 30/19/2016
| venda | 10 | TODO |  |  | MARCOS/JULIO |  | 30/19/2016
FAZER ATA |  | 2 |  |  | DONE | LUIS | 21/19/2016 |  | 21/19/2016
FAZER STATUSREPORT |  | 2 |  |  | DONE | LUIS | 21/19/2016 |  | 21/19/2016
FAZER BACKLOG |  | 2 |  |  | DONE | PEDRO | 21/19/2016 |  | 21/19/2016

## Cálculos (hidden)
*** Esta planilha deve permanecer oculta ***
|  |  |  | Produto | TRIMESTRE 1 | TRIMESTRE 2 | TRIMESTRE 3 | TRIMESTRE 4 | Total
| 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! |  |  | Outros | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | TOTAL | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!